CmDv’s Annual Fiscal Year Calendar of Events

Activity








2026-2027 Date Range
 
BEGIN FISCAL YEAR







May 1st 

HUD Field Office Audit






May (tba) 

Compile CAPER DRAFT






May 1st 

Send Citizen Advisory Committee meeting reminders


May 11th  

Advertise CAPER (15 days public comment)




May 29th – June 15th    

Citizens Advisory Committee - meeting #1 (review CAPER)


June 11th    
Introduce CAPER to City Council public hearing



June 2nd 

Environmental Review Process (CE, Demo & Rehab projects)

June – July

Adopt CAPER at City Council public hearing




June 2nd  

Enter CAPER in IDIS







June 17th  

HUD 425 Report due (Apr 1-June 30)





July 20th
CAPER final submittal deadline – due in IDIS




July 29th 
HUD 60002 and Section 3 Report (due with CAPER)



July 30th 

HOME Project commitment deadline (for two years prior funds)

July 31st 

HUD 4710 Report (Davis Bacon) – due in IDIS (Apr 1-Sept 30)

October 15th 
HUD 2516 Report (MBE) – due in IDIS (Oct 1 – Sept 30)


October 15th
HUD 425 Report (July 1-Sept 30)





October 19th
Prepare Annual Plan (budget & activity proposal for following year)
November – March
Collect Non-Profit input for Annual Plan




November 2nd – 16th 

Neighborhood Meeting – Groups AB, C, D, E, & F (for Annual Plan)

November 4th  
Compile Annual Action Plan DRAFT





November 18th  

Advertise Annual Action Plan (30 days public comment)


December 1st – January 4th  

Citizens Advisory Committee - meeting #2




January 14th
HUD 425 Report due (Oct 1-Dec 31)





January 19th   

Confirm HUD allocations for next fiscal year




February (tba)

Introduce Annual Plan to City Council public hearing (after allocations)
February 4th 

Pay any outstanding CDBG invoices (for Timeliness Test)


February 16th 

Adopt Annual Plan at City Council public hearing (after allocations)

February 18th 

Environmental Review Process (2027 demo projects)


March – April 

HUD Timeliness Test (CDBG)






March 1st 
Rehab Program Application Period (1)




tba
Annual Action Plan final - due in IDIS





March 17th (tba)
HOME Projects desk / site monitoring inspections 



April - May 
Prepare CAPER (accomplishments for past years budget & activities)
April – June
HUD 4710 Report (Davis Bacon) – due in IDIS (Oct 1- Mar 31)

April 13th  
Collect Non-Profit input for CAPER





April 16th – May 4th 

HUD 425 Report due (Jan 1-Mar 31)





April 20th
Enter fiscal year program accomplishments in IDIS                                           April 26th – 28th 

END FISCAL YEAR







April 30th 

